## Sheet1
Seq# | Activity Description | Start Date | End Date | Assigned To | Remarks | Risks
1 | Receive clarifications for all questions | 2020-02-25 | 2020-02-26 |  | Waiting for Product Owner
2 | Finalize the dataset , clean the data set | 2020-02-26 | 2020-02-27 |  | Finalized based on discussion with Product Owner
3 | Validate all the needed software | 2020-02-25 | 2020-02-25 |  | Waiting for link to ask for S/W
4 | Build the web app | 2020-03-02 | 2020-03-03
5 | Build Hybrid approach for test data | 2020-03-03 | 2020-03-06
7 | Train the data | 2020-03-05 | 2020-03-07
8 | Finalize code and upload to Git | 2020-03-08 | 2020-03-08
9 | User manual , any other expected deliverable | 2020-03-08 | 2020-03-08
6 | Brainstorm on possible outputs to be presented | Everyday during touchbase meeting
10 | Touchbase meetings | Everyday - 4PM to 4:30 PM

## Kavi_Plan
Phase | Timeline | Tasks
Bootstrap | 25-Feb to 2-March 2020 | 1. Resolve your queries: 26-Feb
2. Define scope for MVP: 27-Feb
3. Provide required Software/Cloud lab details: 27-Feb
4. Design your App: 1-Mar
5. Intermediate review: 2-Mar
Implementation | 3-March to 9-March 2020 | 6. Implement your app: 3-Mar to 8-Mar
7. Demo with problem owners: 9-Mar
Pre-Final | 10-Mar to 13-Mar 2020 | 8. Demonstrate your app to architect panel
Final | 16-Mar to 18-Mar 2020 | 9. Be part of top-3 teams to demonstrate your work on Grand finale
10. Be a champion!!